## GanttChart
Gantt Chart					© 2008 Vertex42 LLC	0
				Download Professional Version for Excel
[Project Name]
[Company Name]

	Project Lead:	John Doe
	Today's Date:	3/27/2017	(Pzt)	(vertical red line)
[42]	Start Date:	1/2/2017	(Pzt)					First Day of Week (Sun=1):	2	1/2/2017	1/3/2017	1/4/2017	1/5/2017	1/6/2017	1/7/2017	1/8/2017	1/9/2017	1/10/2017	1/11/2017	1/12/2017	1/13/2017	1/14/2017	1/15/2017	1/16/2017	1/17/2017	1/18/2017	1/19/2017	1/20/2017	1/21/2017	1/22/2017	1/23/2017	1/24/2017	1/25/2017	1/26/2017	1/27/2017	1/28/2017	1/29/2017	1/30/2017	1/31/2017	2/1/2017	2/2/2017	2/3/2017	2/4/2017	2/5/2017	2/6/2017	2/7/2017	2/8/2017	2/9/2017	2/10/2017	2/11/2017	2/12/2017	2/13/2017	2/14/2017	2/15/2017	2/16/2017	2/17/2017	2/18/2017	2/19/2017	2/20/2017	2/21/2017	2/22/2017	2/23/2017	2/24/2017	2/25/2017	2/26/2017	2/27/2017	2/28/2017	3/1/2017	3/2/2017	3/3/2017	3/4/2017	3/5/2017	3/6/2017	3/7/2017	3/8/2017	3/9/2017	3/10/2017	3/11/2017	3/12/2017	3/13/2017	3/14/2017	3/15/2017	3/16/2017	3/17/2017	3/18/2017	3/19/2017	3/20/2017	3/21/2017	3/22/2017	3/23/2017	3/24/2017	3/25/2017	3/26/2017	3/27/2017	3/28/2017	3/29/2017	3/30/2017	3/31/2017	4/1/2017	4/2/2017	4/3/2017	4/4/2017	4/5/2017	4/6/2017	4/7/2017	4/8/2017	4/9/2017	4/10/2017	4/11/2017	4/12/2017	4/13/2017	4/14/2017	4/15/2017	4/16/2017	4/17/2017	4/18/2017	4/19/2017	4/20/2017	4/21/2017	4/22/2017	4/23/2017	4/24/2017	4/25/2017	4/26/2017	4/27/2017	4/28/2017	4/29/2017	4/30/2017	5/1/2017	5/2/2017	5/3/2017	5/4/2017	5/5/2017	5/6/2017	5/7/2017	5/8/2017	5/9/2017	5/10/2017	5/11/2017	5/12/2017	5/13/2017	5/14/2017	5/15/2017	5/16/2017	5/17/2017	5/18/2017	5/19/2017	5/20/2017	5/21/2017	5/22/2017	5/23/2017	5/24/2017	5/25/2017	5/26/2017	5/27/2017	5/28/2017	5/29/2017	5/30/2017	5/31/2017	6/1/2017	6/2/2017	6/3/2017	6/4/2017	6/5/2017	6/6/2017	6/7/2017	6/8/2017	6/9/2017	6/10/2017	6/11/2017	6/12/2017	6/13/2017	6/14/2017	6/15/2017	6/16/2017	6/17/2017	6/18/2017	6/19/2017	6/20/2017	6/21/2017	6/22/2017	6/23/2017	6/24/2017	6/25/2017	6/26/2017	6/27/2017	6/28/2017	6/29/2017	6/30/2017	7/1/2017	7/2/2017	7/3/2017	7/4/2017	7/5/2017	7/6/2017	7/7/2017	7/8/2017	7/9/2017	7/10/2017	7/11/2017	7/12/2017	7/13/2017	7/14/2017	7/15/2017	7/16/2017	7/17/2017	7/18/2017	7/19/2017	7/20/2017	7/21/2017	7/22/2017	7/23/2017	7/24/2017	7/25/2017	7/26/2017	7/27/2017	7/28/2017	7/29/2017	7/30/2017	7/31/2017	8/1/2017	8/2/2017	8/3/2017	8/4/2017	8/5/2017	8/6/2017	8/7/2017	8/8/2017	8/9/2017	8/10/2017	8/11/2017	8/12/2017	8/13/2017	8/14/2017	8/15/2017	8/16/2017	8/17/2017	8/18/2017	8/19/2017	8/20/2017	8/21/2017	8/22/2017	8/23/2017	8/24/2017	8/25/2017	8/26/2017	8/27/2017
WBS	Tasks	Task Lead	Start	End	Duration (Days)	% Complete	Working Days	Days Complete	Days Remaining		01 - Oca - 00					09 - Oca - 17					16 - Oca - 17					23 - Oca - 17					30 - Oca - 17					06 - Şub - 17					13 - Şub - 17					20 - Şub - 17					27 - Şub - 17					06 - Mar - 17					13 - Mar - 17					20 - Mar - 17					27 - Mar - 17					03 - Nis - 17					10 - Nis - 17					17 - Nis - 17					24 - Nis - 17					01 - May - 17					08 - May - 17					15 - May - 17					22 - May - 17					29 - May - 17					05 - Haz - 17					12 - Haz - 17					19 - Haz - 17					26 - Haz - 17					03 - Tem - 17					10 - Tem - 17					17 - Tem - 17					24 - Tem - 17					31 - Tem - 17					07 - Ağu - 17					14 - Ağu - 17					21 - Ağu - 17

1	<Documentation>		2/08/17	3/06/17	26	100%	19	26	0
1.1	<API Research>		2/08/17	2/11/17	3	100%	3	3	0
1.2	<Project Investigation>		2/14/17	2/19/17	5	100%	4	5	0
1.3	<Communication Plan>		2/22/17	2/23/17	4	100%	2	4	0
1.4	<Software Requirements>		2/28/17	3/06/17	12	100%	5	12	0
1.5	<Use-cases>		2/28/17	3/06/17	4	100%	5	4	0
1.6	<Use-case scenarios>		2/28/17	3/06/17	5	100%	5	5	0
2	<Mock-up Design>		2/28/17	3/09/17	9	100%	8	9	0
2.1	<Web design>		2/28/17	3/09/17	9	100%	8	9	0					1.6					1.6	<Use-case scenarios>		2/28/12	3/04/12	5	100%	4	5	0					1.6	<Use-case scenarios>		2/28/12	3/04/12	5	100%	4	5	0					1.6	<Use-case scenarios>		2/28/12	3/04/12	5	100%	4	5	0
2.1	<Android design>		2/28/17	3/09/17	9	100%	8	9	0
2.2	Milestone 1-Completion of Requirements and Mock-ups		2/08/17	3/09/17	29	100%	22	29	0
3	<Diagrams>		2/28/17	4/23/17	54	54%	39	29	25
3.1	<Use-case diagram>		2/28/17	3/06/17	6	100%	5	6	0
3.2	<Class diagram>		3/07/17	3/12/17	5	100%	4	5	0
3.3	<Sequence diagram>		3/17/17	3/22/17	5	100%	4	5	0
3.4	<Activity diagram>		4/18/17	4/23/17	5	0%
3.5	Milestone 2-Completion of diagrams		2/28/17	4/23/17	54	100%	39	54	0
4	<Planning>		3/14/17	5/02/17	49	0%	36	0	49
4.1	<Initial project plan>		3/14/17	3/19/17	5	100%	4	5	0
4.2	<Responsibility assignment matrix>		4/04/17	4/08/17	4	0%	4	0	4
4.3	<Test plan>		4/28/17	5/02/17	4	0%	3	0	4
5	<Implementation>		5/05/17	12/14/17	223	0%	160	0	223
5.1	<Learn Android application coding>		5/05/17	9/02/17	120	0%	86	0	120
5.2	<Learn web coding>		5/05/17	9/02/17	120	0%	86	0	120
5.3	<Learn more about back-end development>		5/05/17	9/02/17	120	0%	86	0	120
5.4	Milestone 3-Learning coding		5/05/17	9/02/17	120	0%	86	0	120
5.5	<Implementation of user class>		9/23/17	9/30/17	7	0%	5	0	7
5.6	<Implementation of Authentication class>		9/30/17	10/07/17	7	0%	5	0	7
5.7	<Implementation of sign-up>		10/07/17	10/14/17	7	0%	5	0	7
5.8	<Implementation of sign-in>		10/07/17	10/14/17	7	0%	5	0	7
5.9	<Implementation of home page>		10/14/17	10/21/17	7	0%	5	0	7
5.10	<Implementation of profile page>		10/14/17	10/21/17	7	0%	5	0	7
5.11	Milestone 4-Implementation of basic classes and pages		9/23/17	10/21/17	28	0%	20	0	28
5.12	<Implementation of comment and annotation classes>		10/21/17	10/28/17	7	0%	5	0	7
5.13	<Implementation of tag and date classes>		10/28/17	11/04/17	7	0%	5	0	7
5.14	<Implementation of media item class>		11/02/17	11/09/17	7	0%	6	0	7
5.15	<Implementation of cultural heritage item class>		11/09/17	11/16/17	7	0%	6	0	7
5.16	<Implementation of recommendation manager>		11/16/17	11/30/17	14	0%	11	0	14
5.17	<Implementation of search manager>		11/30/17	12/14/17	14	0%	11	0	14
5.18	Milestone 5-Completion of implementation		10/21/17	12/14/17	54	0%	39	0	54

HELP / - Modify the GREEN cells and the WBS, Tasks, and Task Lead columns. The rest of the columns are formulas. / - The number of weeks shown in the gantt chart is limited by the maximum number of columns available. / - The Start Date that you choose determines the first week in the gantt chart, starting on a Monday. / - Change the first day of the week via cell K8 / - Use the slider to adjust the range of dates shown in the gantt chart. / - Only 34 weeks can be shown/printed at one time, because each week uses up 7 columns. / Q: How do I make Task 2 start the day after the end of Task 1? / Use the following formula for the start date of Task 2: / =EndDate+1 / where EndDate is the reference to the cell containing the end date of task 1 / Q: How do I add/insert tasks and subtasks? / Copy the entire ROW (or a group of rows) for the type of task(s) you want to add and then right-click on the row where you want to insert the new tasks, then select Insert Copied Cells. / Important Note: When inserting a new subtask after the last subtask or before the first subtask, you will need to update the formulas for calculating the Level 1 %Complete and Duration (see below) to include the new subtask, because the ranges won't automatically expand to include the additional row. / Q: How do I calculate the %Complete for a Level 1 task based upon the %Complete of all of the associated subtasks? / Example: If Task 1 is on row 11 and the subtasks are on rows 12-15, use the following formula: / =SUMPRODUCT(F12:F15;G12:G15)/SUM(F12:F15) / Q: How do I calculate the Duration for a Level 1 task based upon the largest end date of a sub task? / Example: If the Level 1 task is on row 11 and the sub tasks are on rows 12-15, use the following formula / =MAX(E12:E15)-D11 / Q: How can I include holidays in the calculation of the Working Days? / You can add a list of holidays to exclude in the NETWORKDAYS function. See the help on that function. / Q: How do I change the print settings? / Select the entire range of cells that you want to print and then define a Print Range in the Format menu. Then go to Format > Page and select the Sheet tab. Adjust the Scaling mode as desired.